## Slide 1: Polk County - Ocoee Corridor K
US-64/SR-40
September 10, 2024

## Slide 2: Background
Part of the Appalachian Development Highway System (1965)
Safe and reliable east-west route
Improve mobility and connectivity in the area
Multiple previous attempts to develop projects in the corridor
Notes: Corridor K originally proposed in Appalachian Regional Development Act in 1965 as part of the Appalachian Development Highway System (ADHS)
From I-75 near Cleveland, TN to Dillsboro, NC.
Goal of the ADHS is to generate economic development across Appalachia by providing access to regional and national markets and provide growth opportunities.
This section of Corridor K is one of the last incomplete sections.
Originally proposed as a 4-lane divided, 50 mph facility.
Numerous efforts to develop project hindered by cost and other constraints.

## Slide 3: US-64/SR-40 “Corridor K” - TDOT History
Corridor K is one of 31 projects originally listed in ARDA
1965
1970s
1980s
1990s
1999
TDOT begins planning work
(including NEPA)
Project does not advance due to lack of funding
TDOT/FHWA develop EA, approved-1990.
FONSI never approved. 1993 project placed on indefinite hold
TDOT/USFS prepare EA/FONSI.
  Due to Financial/Environmental Cost to Benefit Ratio, FHWA does not adopt EA/FONSI
  TDOT/FHWA initiate EIS
Cost and issues raised by public, interest groups, resource agencies lead to rescission of DEIS
2008
2009
2009/10
2014 –17
2018
Current EIS planning & NEPA begins
2022
  Major Rockslide
Adding long tunnel option developed & distributed.
Targeted Approach Developed & Pauses current EIS
ARC gives TDOT approval to move forward with Public Outreach Targeted Approach
2020
ARC approved change from new alignment to targeted approach
Notes: Started and stopped several Environmental Documents.
Most recent effort initiated in 2009 included 7 proposed options, including a 6-mile tunnel (likely favored option) which had an estimated cost of over $2 billion.
Rockslide – Route was detoured for over a year - 70 mile / 1.5 hour long detour.
While road was closed down, TDOT maintenance forces improved the radius of one of the curves.
In 2018, TDOT started pursuing a Targeted Approach for the Corridor. The ARC approved the Targeted Approach earlier this year.

## Slide 4: US-64/SR-40 “Corridor K”
CHALLENGES
  Located in Cherokee National Forest
  Environmental Constraints
  Topography
  Cost
TARGETED APPROACH
  Multiple projects to address needs of corridor
  35 Road Safety Audit Projects
  14 Rockfall Mitigation Sites
Notes: Numerous issues affected environmental review of project:
Cherokee National Forest – unique requirements, such as aesthetics, for projects within the forest and their own environmental processes
Alphabet soup of other agencies – ARC, FHWA,
Three dams along the river, so have to work with the TVA
Endangered species, pyritic material, TWRA, USFWS, TDEC, etc.
River on one side, mountains on the other
Recreation, including whitewater rafting, is a major economic driver for the area
Challenges in maintaining access for all the recreational traffic
In 2018, TDOT decided to take a fresh look at the Corridor to determine if something could be done to the existing facility to improve the safety and reliability and meet the intent of the ADHS.
We found that transportation deficiencies were more localized than system-wide.
Developed the Targeted Approach which included 35 projects to address specific needs of the corridor, such as improving some horizontal curves, mitigating potential rockfall hazards, and adding shoulders and turn lanes.

## Slide 5: US-64/SR-40 “Corridor K” Overview
Targeted
Approach
CORRIDOR K
SR-40 (US-64) From West of the Ocoee River to SR-68 Near Ducktown
Polk County, TN,
PIN 102420.08

## Slide 6: Traffic/Safety
Safety First
  Drives many of the improvements
  Geometric deficiencies
  Parking/Pedestrians
Traffic Characteristics
  Regional Corridor
  5,000 – 6,000 ADT
  9-10% Trucks

## Slide 7: Targeted Approach
Geometric improvements
Signage/pavement markings
Guardrail
Rockfall/geotechnical improvements
Intersection improvements

## Slide 8: Programmed Projects
In 2023 and 2024 four projects were chosen to progress toward implementation
All four currently in the environmental studies and engineering phases
Location 3
Location 4
Location 7
Location 9

## Slide 9: Location 3
Approx. 1.1 mile widening to 3 lanes with paved shoulders
10’ shared use path on south side to connect existing maintenance road west of Welcome Valley Road that connects to Ocoee River
200’ Cloud Branch Bridge Replacement
Geometric Improvements
45 mph design speed
ROW – FY 2025
Construction – FY 2026

## Slide 10: Location 3

## Slide 11: Location 3

## Slide 12: Location 3

## Slide 13: Location 4
Intersection Improvements
  Realigning SR-314 (Parksville Road) to provide safer turning movements
Widening SR 40 to 3 lanes and 6’ shoulders
Adds 10’ shared use path to provide access between Ocoee River and Sugarloaf Mountain Park
Consolidate access drives for TVA and Sugarloaf Mountain Park to simplify/improve ingress/egress
ROW – FY 2025
Construction – FY 2026

## Slide 14: Location 4

## Slide 15: Location 7
Improve traffic flow/circulation around high activity center
Improve horizontal curve to 35mph
Add new entrance to marina with dedicated eastbound right turn and westbound left turn
Convert existing driveway that is both entry and exit to marina to exit only
ROW – FY 2026
Construction – FY 2027

## Slide 16: Location 7

## Slide 17: Location 7

## Slide 18: Location 9
Improve traffic flow/circulation around USFS Ranger Station and Oswald Road
Consolidating Ranger Station access to Oswald Road
Adding EB left turn lane onto Oswald
ROW – FY 2026
Construction – FY 2027

## Slide 19: Location 9

## Slide 20: Next Steps
Finalize preliminary engineering, incorporating environmental features for Locations 3 and 4
Complete environmental studies for Locations 3, 4, 7, and 9
Continue design process for Locations 3, 4, 7, and 9
Advance all 4 projects to construction
Begin Development of Design Plans and Environmental Studies for Additional Locations
What to expect next as property owners
  Be on the lookout for survey crews, ecologists, archaeologists, etc.
  If driving in the corridor, be on the lookout for workers

## Slide 21: Future Projects
Targeted Approach Location | Project Type
Location 5 | Geometric Improvement
Locations 10 and 12 | Geometric Improvements
Locations 13 – 18 | Geometric and rockfall mitigation
Locations 19 – 22 | Geometric and rockfall mitigation
Locations 23 – 25 | Geometric and rockfall mitigation
Locations 26 – 30 | Geometric and rockfall mitigation
Locations 31 and 32 | Geometric and rockfall mitigation

## Slide 22: More Information

## Slide 23: Thank You